## Test Plan CDBR
Abbreviated Test Plan for CDBR EDI - Enrollment and Billing (if testing already completed for CDRR EDI)
Supplier
Date Completed
TP #4 High Level Information: |  |  |  |  | Test Plan #4 - CRES sends an enrollment request (814e) with secondary request for summary interval meter information and HI detail historical information. EDU replies with an enrollment response (814er) accepting the enrollment. EDU sends second month usage. CRES responds with second month invoice with correction to first month invoice. Meter Type: Interval Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 929600 |  |  |  |  | Billing: Test an original billing of interval meter with summary usage.
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
4 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request with secondary request for summary interval meter information. | 814e created and sent to EDU REF02=SUMMARY
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | 2012-04-03 | Usage/Interval- EDU will send interval usage summarized on a monthly usage transaction | 867
| F4 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F5 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to EDU
| F6 | Utility | 820 | 2012-05-27 | Remittance- EDU will send first month remittance detail. ACH payment will NOT be tested; only remittance detail. IF 820CTX is used then send prenote through the bank with at least one payment | 820 created and sent to CRES |  | step will be skipped
| F7 | Utility | 867 | 2012-06-24 | Usage/Monthly - EDU will send second month usage | 867created and sent to CRES
| F8 | Supplier | 810 | 2012-06-25 | Invoice- CRES will send invoice for second month usage which includes a correction for the first month invoice rate. NOTE: the correction on the second month's invoice will be additional SAC segment(s) correcting the rate sent in the first month 810. | 810 created and sent to EDU
TP #6 High Level Information: |  |  |  |  | Test Plan #6 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Test a change to CRES account number. CRES responds with Bill Ready 810 Outside Bill Window. EDU responds with 824. EDU sends second month usage. CRES responds with invoice for first and second month. Meter Type: Interval Billing Options: LDC Bill Ready |  |  | Notes:
Account No: 611000 |  |  |  |  | Billing: Test an original billing with no usage in first month and two months of usage in second month.
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
6 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Supplier | 814c | 2012-04-06 | Change Request- CRES sends change of CRES account number | 814c created and sent by CRES
| F4 | Utility | 814cr | 2012-04-06 | Change Response - EDU response accepting supplier account number change | 814cr created and sent by EDU
| F5 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F6 | Supplier | 810 | 2012-06-01 | Invoice- CRES will send first month invoice, Outside Bill Window | 810 created and sent to EDU
| F7 | Utility | 824 | 2012-06-01 | Application Advice from EDU for Invoice Received Outside Bill Window | 824 created and sent to CRES with rejection of outside bill window
| F8 | Utility | 867 | 2012-06-24 | Usage/Monthly - EDU will send second month usage | 867created and sent to CRES
| F9 | Supplier | 810 | 2012-06-25 | Invoice- CRES will send first and second month invoices | Two 810s created and sent to EDU within current open Bill Window. |  | DP&L will reject 810s sent outside bill window, so CRES will need to resend first month.
TP #7 High Level Information: |  |  |  |  | Test Plan #7 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Utility sends a change in customer mailing address. CRES responds with 814 response. Utility bills and send 867 usage. CRES returns Bill Ready 810 with details not equal to total. EDU responds with 824. CRES sends corrected 810 within open bill window. Meter Type: Single Kwh Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 1801966802 |  |  |  |  | Billing: Test a change in customer mailing address, invalid supplier invoice amount & corrected invoice amount
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
7 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | 2012-04-06 | Change in Customer mailing address. | 814c created and sent to CRES
| F4 | Supplier | 814cr | 2012-04-06 | Accept Response | 814cr created and sent to EDU
| F5 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send usage | 867 created and sent to CRES
| F6 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice with details not summing to total | 810 created and sent to EDU
| F7 | Utility | 824 | 2012-05-27 | Application Advice from EDU for Invoice Details not summing to total | 824 created and sent to CRES with reject code "SUM"
| F8 | Supplier | 810 | 2012-05-29 | Invoice- CRES will send corrected first month invoice within current open bill window. | Corrected 810 created and sent to EDU |  | Bill messages will be displayed from 810 for current bill month - note only messages on current 810s will be displayed on bill.
TP #8 High Level Information: |  |  |  |  | Test Plan #8 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU sends 867 monthly usage. CRES responds with Bill Ready 810. EDU sends 867 Cancel and new (rebill) 867. CRES responds with 810 Cancel and new (rebill) 810. Meter Type: Multiple meters (Kwb/Kw and Unmetered) Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 501969041 |  |  |  |  | Billing: Test an original billing. Test cancel and restate of original billing due to an incorrect read.
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
8 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F4 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to EDU
| F6 | Utility | 867 (Can) | 2012-05-28 | Usage/Monthly- EDU will cancel first month usage | 867 created and sent to CRES
| F6 | Utility | 867 (Rebill) | 2012-05-28 | Usage/Monthly- EDU will restate first month usage | 867 created and sent to CRES
| F7 | Supplier | 810 (Can) 810 (Rebill) | 2012-05-29 | Invoice- CRES will restate first month invoice | 810 created and sent to EDU
TP #10 High Level Information: |  |  |  |  | Test Plan #10 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Meter Type: Time of Day (On and Off Peak meter) Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 743100 |  |  |  |  | Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
10 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | 2012-05-26 | Usage/Monthly - EDU will send first month usage | 867created and sent to CRES
| F4 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to CRES
TP #13 High Level Information: |  |  |  |  | Test Plan #13 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU removed the second meter and will request meter removal from the account (814c). CRES replies with a change response (814cr) accepting the change. Account is billed and is on budget bill. Budget bill message is included in 810. Meter Type: kWh and unmetered Billing Option: LDC Bill READY |  |  | Notes: Suppliers are not required to support this. Budget bill information will be passed in the note fields.
Account No: 1172261656 |  |  |  |  | Billing: Test budget billing
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
13 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | 2012-04-06 | Change from EDU for electric meter removal only | REF TD = NM1MR
| F4 | Supplier | 814cr | 2012-04-06 | Change from EDU Response- CRES sends response accepting change | Ex: ASI = ASI*WQ*001
| F5 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F6 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice with budget bill information in bill messages. | 810 created and sent to EDU
TP #14 High Level Information: |  |  |  |  | Test Plan #14 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU removed the nightlight and will request meter removal from the account (814c). CRES replies with a change response (814cr) accepting the change. EDU sends 867 usage. CRES responds with Bill Ready 810. EDU sends second month usage. CRES responds with (17) cancel for the original 810, and a re-issue (18) 810 with the correction to first month invoice (CRES rate). In addition, the second month invoice is sent. Meter Type: kWh and unmetered Billing Option: LDC Bill READY |  |  | Notes: Suppliers are not required to support 810 17 & 18s.
Account No: 5059759827 |  |  |  |  | Billing:
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
14 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | 2012-04-06 | Change from EDU for nightlight removal only | REF TD = NM1MR
| F4 | Supplier | 814cr | 2012-04-06 | Change from EDU Response- CRES sends response accepting change | Ex: ASI = ASI*WQ*001
| F5 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F6 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to EDU
| F7 | Utility | 867 | 2012-06-24 | Usage/Monthly - EDU will send second month usage | 867created and sent to CRES
| F8 | Supplier | 810 C -17 810 R - 18 | 2012-06-25 | Invoice- CRES will restate first month invoice 810 R - 18 Includes a correction for the first month invoice rate. Must send 17 before 18. | 810s created and sent to EDU
| F8 | Supplier | 810 | 2012-06-25 | Invoice- CRES will send invoice for second month usage | 810 created and sent to EDU
TP #15 High Level Information: |  |  |  |  | Test Plan #15 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU sends monthly usage (867). CRES responds with bill ready invoice (867). EDU sends remittance detail (820). Meter Type: Multiple meters (Kwh and Two Night Lights) Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 499395798 |  |  |  |  | Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
15 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F4 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to EDU
| F5 | Utility | 820 | 2012-05-28 | Remittance- EDU will send first month remittance detail. ACH payment will NOT be tested; only remittance detail. | 820 created and sent to CRES
TP #16 High Level Information: |  |  |  |  | Test Plan #16 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Utility sends a meter exchange. Meter Type: Single Kwh Billing Option: LDC Bill Ready |  |  | Notes:
Account No: 634622858 |  |  |  |  | Billing: Test meter exchange
Test# | Frame | Responsibility | Transaction | Process Date | Description of Frame | Expected Results | Actual Results
16 | F1 | Supplier | 814e | 2012-04-03 | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | 2012-04-03 | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | 2012-05-26 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F4 | Supplier | 810 | 2012-05-27 | Invoice- CRES will send first month invoice | 810 created and sent to EDU
| F5 | Utility | 814c | 2012-05-28 | Change in a meter exchange | 814c created and sent to CRES
| F6 | Supplier | 814cr | 2012-05-29 | Accept Response | 814cr created and sent to EDU
| F7 | Utility | 867 | 2012-06-24 | Usage/Monthly- EDU will send second month usage with usage from old and new meter. | 867 created and sent to CRES
| F8 | Supplier | 810 | 2012-06-25 | Invoice- CRES will send second month invoice | 810 created and sent to EDU

## Summary
TP | Description | Account # | Last Name | First Name | Company Name
4 | Enrollment Accepted with historical usage Interval Meter. Two months usage and invoicing | 929600 |  |  | Practical Solutions INC
6 | Enrollment, Change Cres Acct number, first billing send 810 outside billing window, second billing, send in previous and current months 810s. | 611000 |  |  | Secrets Actors Assoc
7 | Enrollment, then utility changes customer address; CRES sends in bill correction in SAC line in 810. | 1801966802 | Maxwell | Xavier
8 | Enrollment with multiple meters, invoice and cancel/rebill. | 501969041 | Paul | Carson
10 | Enrollment and billing transactions with TOU meters | 743100 |  |  | Middletown Eats and Sleep
13 | Enrollment with unmetered and metered services then meter removed, billing after and is on budget bill. | 1172261656 |  |  | Big Tent House
14 | Enrollment with unmetered and metered services then unmetered removed, billing after. Process 17 and 18 810s. Two months usage and invoicing | 5059759827 |  |  | Susans Modeling Agency
15 | Enrollment metered and two Night Lights, billing transactions and payment | 499395798 |  |  | Woodward Academy
16 | Enrollment, billing, meter exchange, and then billing on new meter. | 634622858 | Spencer | Malcolm

## Supplier Request 4 (hidden)
Test Case | Frame | Who | What | Comment
3 | F4 | Supplier | 810
4 | F5 | Supplier | 810
6 | F6 | Supplier | 810
7 | F6 | Supplier | 810
8 | F4 | Supplier | 810
9 | F4 | Supplier | 810
9 | F4 | Supplier | 814d
11 | F4 | Supplier | 810
12 | F3 | Supplier | 814d
13 | F6 | Supplier | 810
14 | F6 | Supplier | 810
15 | F4 | Supplier | 810
16 | F4 | Supplier | 810