## Test Plan EDI Ohio
Ohio Test Plan for EDI Certification - Enrollment and Billing
Supplier
Date Completed
TP #1 High Level Information: |  |  |  | Test Plan #1 - CRES sends an enrollment request (814e) in order to enroll a customer; however, the account number on the 814e can not be found in EDU's customer database as a valid account number. Therefore, this enrollment request must be rejected. Meter Type: Single Billing Option: LDC Rate Ready |  |  | Notes
Account No: 1300733333
Test # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
1 | F1 | Supplier | 814e | Enrollment - Create and send enrollment request with an account number that does not exist in EDU's customer database | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back a response rejecting the enrollment due to an invalid account number | REF02 = A76 (Reject Reason Code), REF03 = Account Not Found
TP #3 High Level Information: |  |  |  | Test Plan #3 - CRES sends an enrollment request (814e) for a customer with secondary request for historical usage information. The EDU replies with an enrollment response (814er) accepting the enrollment, along with historical usage information (867hu). Meter Type: Single Kwh/Kw Billing Option: LDC Rate Ready |  |  | Notes
Account No: 1500790363
Billing: Test an original billing. Test cancel and restate of original billing due to an incorrect read.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
3 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for historical usage. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request and historical usage request | 814er created and sent to CRES
| F2 | Utility | 867 | Hist Usage- EDU send 12 month historical usage information to CRES | 867 created and sent to CRES BPT01=52
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 867 | Usage/Monthly- EDU will cancel first month usage | 867 created and sent to CRES
| F4 | Utility | 810 | Invoice- EDU will cancel first month invoice | 810 created and sent to CRES
| F5 | Utility | 867 | Usage/Monthly- EDU will restate first month usage | 867 created and sent to CRES
| F5 | Utility | 810 | Invoice- EDU will restate first month invoice | 810 created and sent to CRES
TP #4 High Level Information: |  |  |  | Test Plan #4 - CRES sends an enrollment request (814e) with secondary request for summary interval meter information and HI detail historical information. EDU replies with an enrollment response (814er) accepting the enrollment. Meter Type: Interval Billing Option: LDC Rate Ready |  |  | Notes
Account No: 929600
Billing: Test an original billing of interval meter with summary usage.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
4 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for summary interval meter information. | 814e created and sent to EDU REF02=SUMMARY
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Interval- EDU will send interval usage summarized on a monthly usage transaction | 867
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
TP #8 High Level Information: |  |  |  | Test Plan #8 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Test a change to CRES account number. Meter Type: Single KWH/KW Billing Options: LDC Rate Ready |  |  | Notes
Account No: 1932539962
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
8 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Supplier | 814c | Change Request- CRES sends change of CRES account number | 814c created and sent by CRES
| F4 | Utility | 814cr | Change Response - EDU response accepting supplier account nunmber change | 814cr created and sent by EDU
| F5 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867mu created and sent to CRES
| F5 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
TP #9 High Level Information: |  |  |  | Test Plan #9 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Meter Type: Multiple meters (Kwh/Kw and Unmetered) Billing Option: LDC Rate Ready |  |  | Notes
Account No: 501969041
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
9 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 820 | Remittance- EDU will send first month remittance detail. ACH payment will NOT be tested; only remittance detail. IF 820CTX is used then send prenote through the bank with at least one payment (payment and ACH deposit should not equal for this test) | 820 created and sent to CRES
TP #11 High Level Information: |  |  |  | Test Plan #11 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. CRES drops customer after 1 month service. EDU sends customer's unpaid balance back to CRES for collection. Meter Type: Single Kwh/Kw Billing Option: LDC Rate Ready |  |  | Notes
Account No: 1101998807
Billing: Test an original billing and final bill. EDU to send final balance to CRES for collection.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
11 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Supplier | 814d | Drop from Supplier- CRES requests to drop the customer | REF02 = B38 (Dropped by customer request)
| F5 | Utility | 814dr | Drop from Supplier Response- EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
| F6 | Utility | 867 | Usage/Monthly- EDU will send final month usage | 867 created and sent to CRES
| F6 | Utility | 810 | Invoice- EDU will send final month invoice | 810 created and sent to CRES
| F7 | Utility | 248 | EDU send customer final balance to CRES for collection | 248 created and sent to CRES
TP #12 High Level Information: |  |  |  | Test Plan #12 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Meter Type: Time of Day (On and Off Peak meter) Billing Option: LDC Rate Ready |  |  | Notes
Account No: 743100
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
12 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly - EDU will send first month usage | 867created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
TP #13 High Level Information: |  |  |  | Test Plan #13 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU then requests to drop the customer (814d). CRES replies with a drop response (814dr) acknowledging the drop. Customer recinds the drop and the EDU sends an 814r to the CRES. CRES replies with a response acknowledging reinstatement (814rr). Meter Type: Single Billing Option: LDC Rate Ready |  |  | Notes
Account No: 2365676413
Billing: None
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
13 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment | 814er created and sent to CRES
| F3 | Utility | 814d | Drop from Utility- EDU requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request)
| F4 | Supplier | 814dr | Drop from Utility Response- CRES sends response accepting drop | Ex: ASI = ASI*WQ*024
| F5 | Utility | 814r | Reinstatement- EDU sends requests to reinstate the customer | Ex: ASI = ASI*7*025
| F6 | Supplier | 814rr | Reinstatement Response- CRES sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
TP #14 High Level Information: |  |  |  | Test Plan #14 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. CRES sends requests to drop the customer (814d). EDU replies with a drop response (814dr) acknowledging the drop. CRES errored and rescinds the drop and the CRES sends an 814r to the EDU. EDU replies with a response acknowledging reinstatement (814rr). Meter Type: Single Billing Option: LDC Rate Ready |  |  | Notes
Account No: 582000
Billing: None
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
14 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment | 814er created and sent to CRES
| F3 | Supplier | 814d | Drop from Supplier- Supplier requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request)
| F4 | Utility | 814dr | Drop from CRES Response- EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
| F5 | Supplier | 814r | Reinstatement- CRES sends requests to reinstate the customer | Ex: ASI = ASI*7*025
| F6 | Utility | 814rr | Reinstatement Response- EDU sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
TP #16 High Level Information: |  |  |  | Test Plan #16 modified - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU removed the second meter and will request meter removal from the account (814c). CRES replies with a change response (814cr) accepting the change. Meter Type: kWh and unmetered Billing Option: LDC RATE READY |  |  | Notes
Account No: 1172261656
Billing: None
Test Acct # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
16 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | Change from EDU for electric meter removal only | REF TD = NM1MR
| F4 | Supplier | 814cr | Change from EDU Response- CRES sends response accepting change | Ex: ASI = ASI*WQ*001
| F5 | Utility | 867 | Usage/Monthly- EDU will send final month usage | 867 created and sent to CRES
| F6 | Utility | 810 | Invoice- EDU will send final month invoice | 810created and sent to CRES
TP #17 High Level Information: |  |  |  | Test Plan #17 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU sends 867 monthly usage. CRES responds with Bill Ready 810. EDU sends 867 Cancel and new (rebill) 867. CRES responds with 810 Cancel and new (rebill) 810. Billing Option: LDC BILL READY |  |  | Notes
Account No: ??
Billing: Bill Ready
Test Acct # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
17 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly - EDU will send first month usage | 867created and sent to CRES
| F4 | Supplier | 810 | Invoice- CRES will send first month invoice with details not summing to total | 810 created and sent to EDU
| F5 | Utility | 867 C | Usage/Monthly- EDU will cancel first month usage | 867 created and sent to CRES
| F6 | Utility | 867 (Rebill) | Usage/Monthly- EDU will restate first month usage | 867 created and sent to CRES
| F7 | Supplier | 810 C 810 (Rebill) | Invoice- CRES will restate first month invoice | 810 created and sent to EDU
TP #17 NEW High Level Information: |  |  |  | Test Plan #17 NEW - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. EDU removed the nightlight and will request meter removal from the account (814c). CRES replies with a change response (814cr) accepting the change. Meter Type: kWh and unmetered Billing Option: LDC RATE READY |  |  | Notes
Account No: 5059759827
Billing: None
Test Acct # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
17 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | Change from EDU for nightlight removal only | REF TD = NM1MR
| F4 | Supplier | 814cr | Change from EDU Response- CRES sends response accepting change | Ex: ASI = ASI*WQ*001
| F5 | Utility | 867 | Usage/Monthly- EDU will send final month usage | 867 created and sent to CRES
| F6 | Utility | 810 | Invoice- EDU will send final month invoice | 810created and sent to CRES
TP #25NEW High Level Information: |  |  |  | Test Plan #25 NEW- CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Meter Type: Multiple meters (Kwh and Two Night Lights) Billing Option: LDC Rate Ready |  |  | Notes
Account No: 499395798
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
25 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 820 | Remittance- EDU will send first month remittance detail. ACH payment will NOT be tested; only remittance detail. | 820 created and sent to CRES
TP #26High Level Information: |  |  |  | Test Plan #26 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. CRES sends a change in CRES pricing option (814c). EDU replies with a Change response (814cr) Meter Type: Single Kwh Billing Option: LDC Rate Ready |  |  | Notes
Account No: 511519304
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
26 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Supplier | 814c | Change in CRES pricing option | 814c created and sent to EDU
| F5 | Utility | 814cr | Change from CRES Response- EDU sends response accepting change | 814er created and sent to CRES
| F6 | Utility | 867 | Usage/Monthly- EDU will send secondt month usage | 867 created and sent to CRES
| F7 | Utility | 810 | Invoice- EDU will send second month invoice | 810 created and sent to CRES
TP #27High Level Information: |  |  |  | Test Plan #27 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Utility sends a change in customer mailing address. Meter Type: Single Kwh Billing Option: LDC Rate Ready |  |  | Notes
Account No: 1801966802
Billing: Test a change in customer mailing address
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
27 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 814c | Change in Customer mailing address. | 814c created and sent to CRES
| F5 | Supplier | 814cr | Accept Response | 814cr created and sent to EDU
| F6 | Utility | 867 | Usage/Monthly- EDU will send secondt month usage | 867 created and sent to CRES
| F7 | Utility | 810 | Invoice- EDU will send second month invoice | 810 created and sent to CRES
TP #28High Level Information: |  |  |  | Test Plan #28 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Utility sends a meter exchange. Meter Type: Single Kwh Billing Option: LDC Rate Ready |  |  | Notes
Account No: 634622858
Billing: Test meter exchange
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
28 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 814c | Change in a meter exchange | 814c created and sent to CRES
| F5 | Supplier | 814cr | Accept Response | 814cr created and sent to EDU
| F6 | Utility | 867 | Usage/Monthly- EDU will send second month usage with usage from old and new meter. | 867 created and sent to CRES
| F7 | Utility | 810 | Invoice- EDU will send second month invoice | 810 created and sent to CRES
TP #29High Level Information: |  |  |  | Test Plan #29 - CRES sends an enrollment request (814e). EDU replies with an enrollment response (814er) accepting the enrollment. Utility sends in an additional service (Nightlight) Meter Type: Single Kwh Billing Option: LDC Rate Ready
Account No: 636967471
Billing: Test adding an additional service
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
29 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F3 | Utility | 810 | Invoice- EDU will send first month invoice | 810 created and sent to CRES
| F4 | Utility | 814c | Additional service (nightlight) is added to the account | 814c created and sent to CRES
| F5 | Supplier | 814cr | CRES sends acceptance of new nightlight to the account | 814cr created and sent to EDU
| F6 | Utility | 867 | Usage/Monthly- EDU will send second month usage with usage from Electric and new nightlight.. | 867 created and sent to CRES
| F7 | Utility | 810 | Invoice- EDU will send second month invoice for both EL and nightlight services. | 810 created and sent to CRES

## Summary
TP | Description | Account # | Last Name | First Name | Company Name
1 | Enrollment Rejection - Bad Account Number | 1300733333 | Doe | Jonathan
3 | Enrollment Accepted with historical usage, invoice and cancel-rebill | 1500790363 | Woods | Aaron
4 | Enrollment Accepted with historical usage Interval Meter | 929600 |  |  | Practical Solutions INC
5 | Enrollment Accepted, Budget Billing, and CRES Drop | 1189375617 |  |  | Quick Mart Stores
8 | Change CRES Account number | 1932539962 |  |  | Club Flyers
9 | Enrollment with multiple meters, invoice and payment | 501969041 | Paul | Carson
11 | Enrollment and billing transactions, drop and wipe-off | 1101998807 | Palmer | Gregory
12 | Enrollment and billing transactions with TOU meters | 743100 |  |  | Middletown Eats and Sleep
13 | Enrollment, Drop and reinstatement from EDU | 2365676413 |  |  | Bert & Ernie Inc
14 | Enrollment, Drop and reinstatement from CRES | 582000 |  |  | Mainville Ergent Care
16 | Enrollment with unmetered and metered services then meter removed, billing after | 1172261656 |  |  | Big Tent House
17 | Enrollment with unmetered and metered services then unmetered removed, billing after | 5059759827 |  |  | Susans Modeling Agency
25 | Enrollment metered and two Night Lights, billing transactions and payment | 499395798 |  |  | Woodward Academy
26 | Enrollment, CRES changes price option, then billing transactions with new price | 511519304 | Smith | Jimmy
27 | Enrollment, then utility changes customer name and address | 1801966802 | Maxwell | Xavier
28 | Enrollment and then meter exchange | 634622858 | Spencer | Malcolm
29 | Enrollment, billing, then adding another service (NL), then billing again | 636967471 | Jones | Woodrow